UNIVERSITY OF FLORIDA  |  FYCS NON-THESIS PROJECT

Project Command Center

Bridging the Accommodation Gap: Research → Publication → Applied Technology

| PROJECT PHASE BUILD Fall 2026 | SCHOLARLY OUTPUTS 3 + 1 3 papers + EDIS | APPLIED PRODUCT 1 Access & Transition Hub | FINAL DEFENSE SPR 27 FYC 6912 |
| --- | --- | --- | --- |

# Executive Snapshot

The project is now a coherent research-to-practice sequence rather than a single paper. Paper 1 establishes the transition and access needs; Paper 2 tests the existing resource landscape and identifies residual gaps; Paper 3 will convert verified gaps into a bounded student-centered framework and technology demonstration. The EDIS manuscript translates the research for families and practitioners.

RESEARCH-TO-PRACTICE ARCHITECTURE

| PAPER 1 Needs | → | PAPER 2 Gaps | → | PAPER 3 Response | → | HUB Practice |
| --- | --- | --- | --- | --- | --- | --- |

## What Dr. Pracht Is Receiving Now

Committee proposal: project scope, research questions, three-paper architecture, applied product, ethics, and timeline.

Paper 1: structured review of self-advocacy, navigation, disclosure, responsibility transfer, and support continuity.

Paper 2: resource and gap analysis moving into publication-development mode.

EDIS/practitioner manuscript: accessible translation of the high-school-to-college transition research.

Dashboard date: September 14, 2026  •  Prepared for Eric S. Fishon and Dr. Dale Pracht

PORTFOLIO STATUS

# Where We Are

| Workstream | Current State | What It Establishes | Next Decision |
| --- | --- | --- | --- |
| Proposal | Committee defense draft | Scope, RQs, methods, ethics, publication architecture | Confirm scope and proposal-defense revisions |
| Paper 1 | Drafted / citation audit | Needs: self-knowledge, advocacy, disclosure, navigation, responsibility, continuity | Verify source-method details; journal target |
| Paper 2 | Drafted → publication development | Residual gaps: fragmentation, translation to action, implementation, continuity | Close resource map; strengthen reproducible method |
| Paper 3 | Planned | Evidence-informed bridge response | Begin only after Paper 2 gap is confirmed |
| EDIS | Publication-style draft | Family/practitioner translation | Editorial review and submission pathway |
| Hub Prototype | Architecture defined | Prepare → Bridge → Navigate; bounded AI | Convert evidence into module specs and clickable demo |

## The Emerging Scholarly Contribution

Access Continuity is the strongest unifying concept now emerging across the project: access is not achieved merely because information, an accommodation, or a technology exists. Meaningful access depends on continuity across recognition, articulation, navigation, implementation, review, and follow-up.

WORKING CONTINUITY PATHWAY

| Recognize | Articulate | Navigate | Advocate | Implement | Review | Escalate |
| --- | --- | --- | --- | --- | --- | --- |

## Guardrails That Stay Fixed

Student-centered, not technology-centered.

Human institutional authority remains intact.

AI may organize, clarify, rehearse, and navigate; it does not diagnose, determine eligibility, prescribe accommodations, or replace disability services.

No claims of effectiveness without future testing.

Current UF work remains non-human-subjects under the proposed design.

PUBLICATION PIPELINE

# Where We Are Going

| PAPER 1 NEEDS Structured review | PAPER 2 GAPS Resource analysis | PAPER 3 DESIGN Applied framework | EDIS TRANSLATE Practice audience |
| --- | --- | --- | --- |

## Publication Development Plan

| Output | Publication Mode | Immediate Work | Definition of Ready |
| --- | --- | --- | --- |
| Paper 1 | Stand-alone scholarly manuscript | Citation/method audit; verify study-design entries; tighten novelty claim | All retained studies verified; method reproducible enough for stated review design; journal selected |
| Paper 2 | Stand-alone resource/gap manuscript | Close resource map; document search/screening; deepen discussion of access continuity | Evidence trail complete; gap claim bounded; practical implications clear |
| Paper 3 | Applied/design manuscript | Derive functions from Papers 1–2; specify accessibility, privacy, human oversight | Every major feature traceable to evidence or clearly labeled design choice |
| EDIS | Practice publication | Edit for Extension audience; simplify without losing accuracy | Plain-language, actionable, source-grounded, publication-formatted |

## How the Pieces Stay Distinct

The project benefits from reuse of evidence without turning every output into the same paper. Paper 1 answers “What needs exist?” Paper 2 asks “What already addresses those needs, and what remains?” Paper 3 asks “What evidence-informed response is justified?” EDIS asks “What should families and practitioners understand and do now?” The prototype demonstrates translation into practice; it is not evidence of effectiveness.

## Advisor Checkpoints

Scope: Is the secondary → transition → early postsecondary boundary appropriately bounded?

Publication: Which journals or outlets should guide final manuscript formatting and authorship decisions?

Methods: Is the structured-review/resource-map rigor sufficient for the intended outlets?

Contribution: Is “Access Continuity” useful as a working synthesis concept, and how cautiously should it be named?

Applied product: Which prototype functions belong in the UF project versus later doctoral/organizational work?

TECHNOLOGY TRANSLATION

# The Applied Hub: Evidence Made Visible

The technology should visibly demonstrate the project’s core argument: AI and digital tools can reduce friction, but the student remains in control and human support remains central.

| PREPARE Before college Know yourself as a learner Recognize barriers Identify what helps Practice self-advocacy | BRIDGE Transition / handoff Understand what changes Prepare disclosure questions Locate disability services Organize documentation | NAVIGATE After enrollment Activate supports Prepare faculty communication Review implementation Escalate when needed |
| --- | --- | --- |

## AI: Show the Technology Without Letting It Take Over

| AI Can Support | AI Must Not Replace |
| --- | --- |
| Clarify complex institutional information | Diagnosis or disability inference |
| Organize student-entered notes and questions | Eligibility or legal determinations |
| Rehearse a self-advocacy conversation | Autonomous accommodation selection |
| Navigate to verified resources | Professional disability-services judgment |
| Create editable summaries or process records | Student agency and final decision-making |

## What “Tech-Forward” Should Look Like in the Project

The visual language of the project should itself model accessible technology: clean information hierarchy, strong contrast, short information blocks, predictable navigation, student-controlled exports, clear AI labels, and visible handoffs to verified human resources. The dashboard, prototype, figures, and publication graphics should use the same design vocabulary so the scholarship and technology feel like one coherent program of work.

EXECUTION ROADMAP

# Next 90 Days

| Window | Primary Focus | Deliverable | Advisor Touchpoint |
| --- | --- | --- | --- |
| Now → late Sept | Proposal + Paper 1 | Resolve committee feedback; complete Paper 1 evidence/citation audit | Confirm scope and Paper 1 publication direction |
| Late Sept → Oct | Paper 2 | Close resource map; strengthen method; integrate strongest higher-ed evidence | Review gap claim and “Access Continuity” framing |
| Oct → Nov | Paper 3 + prototype | Translate verified needs/gaps into framework and bounded demo | Review feature-to-evidence traceability |
| Nov → Dec | Integration | Align terminology, references, figures, manuscripts, EDIS, and prototype documentation | Publication readiness + Spring defense plan |
| Spring 2027 | Completion | Final revisions, defense, signed paperwork | Final defense |

## Decision Log for Eric + Dr. Pracht

□ Confirm final UF scope and population boundary.

□ Confirm whether three-paper architecture is accepted for final non-thesis package.

□ Confirm publication targets / coauthor expectations for Papers 1 and 2.

□ Confirm Paper 2 method/resource-map completion standard.

□ Confirm whether “Access Continuity” remains a working concept or becomes a named framework.

□ Approve Paper 3 build sequence and prototype boundaries.

□ Confirm EDIS submission pathway and relationship to the scholarly papers.

## Source Package in This Review

FYCS Non-Thesis Project Proposal — Committee Defense Draft (September 2, 2026)

Paper 1 — Preparing Students with Invisible Disabilities for Postsecondary Education

Paper 2 — From Information to Access: Structured Resource and Gap Analysis

Paper 2 — Publication Development Draft (JPED-oriented development copy)

EDIS Draft — From High School to College: Building Self-Advocacy, Navigation, and Access

NORTH STAR

Build the evidence first. Verify the gap. Then use accessible technology to make the path easier to understand, navigate, and act on.